## Sheet1
Team #: | P21011 | Team Name: | CHAD 1000
Date: | 2021-05-02 | Document Owner: | Hannah Husarek
Revision #: | 8
ID | Category | Risk Item | Effect | Cause | Likelihood | Severity | Importance | Action to Minimize Risk | Owner | Status
| What type of risk is this? | Describe the risk briefly | What is the effect on any or all of the project deliverables if the cause actually happens? | What are the possible cause(s) of this risk? | L | S | L*S | What action(s) will you take (and by when) to prevent, reduce the impact of, and/or transfer the risk of this occurring? | Who is responsible for following through on mitigation? | Is this risk this active or is it closed out?
1 | Resource | Teammates gets sick/catches Covid -19 | Other teammates will have more work to do, hopefully we can work online. | We are in a pandemic | 9 | 9 | 81 | Continue to follow RIT health policy's | RIT | Closed- no one got sick this year!
2 | Resource | Cannot deliver on some CR becasue of patents or pre exsiting products | Come up with innovations or new ideas | Current products fulfill CR requirments | 6 | 6 | 36 | Team memers will understand current patents | Jared | Closed- we never ran into a patent issue with the design of the device
3 | Technical | Hydraulic system from last year does not function | Project may be delayed while we redesign | It was rusting and sitting in a locker for 6 months | 4 | 4 | 16 | Plan for it not to work intially | Chad | Closed- Analyized last year hydraulic system and we are working on getting both working
4 | Technical, safety | The device is not able to support the weight of the individual | The person could injure themselves | The material chose are not strong enough, the foundation of the device may not be stable enough | 8 | 5 | 40 | Do simulation in the CAD software to make sure the current design can hold up | Gina | Closed- after testing, the device can support up to at least 200 lbs without tipping over
5 | Safety | User could fall if device moves too slowly/quickly | Person will be injured and possibly trapped on the floor | Unbalanced device | 9 | 6 | 54 | Test our product under various loads and constraints | Chad | Closed- the devices operated very slowly, the user will not be launched off the device in its current state
6 | Technical | Device failure could limit access to facilities | The person can no longer use the bathroom | Mechanical failure, Hydraulic failure | 6 | 3 | 18 | Run fluent test to make sure the device is reliable in the field | Kaylie | Closed- the devices can still be used even if the lifting feature become inoperable
7 | Safety, Technical, Environmental | Because of Covid-19, we could not be able to finish a working prototype | There is no working prototype, waste of time and money on materials | Global pandemic still in effect | 9 | 9 | 81 | Team wears masks and follows state and school listed mandates on social distancing | Kaylie | Closed- The team was able to finish the prototype
8 | Resource | Materials may not fit cost requirements | Materials are to compex or exspensive | Shipping cost might increase, using high end materials | 5 | 6 | 30 | "Team will do what they have to do, its a hustle" -Kaylie | Jared | Closed- the team was underbudget for project
9 | Environmental, Safety | Sanitation issues can lead to bacteria build up and corrosion of materials | Device could break and become unusable, health risk to the user | Crevices in device difficult to clean, device life span significantly decreased | 8 | 9 | 72 | Test materials and minimize bacteria hotspots on the device | Kaylie | Closed- biomaterial testing was not conduct but results from papers, showed this is unlikely
10 | Safety, Technical | Device has pinch points | Person will be injured | Moving parts are poorly designed and do not account for the possibility of pinching | 4 | 4 | 16 | Be mindful of pinch points in the design phase | Chad | Closed- team elimanted pinch points were the users, could get caught
11 | Technical | User has difficulty transporting the device | The time benefit of using the device will be reduced | Device is too heavy or unwieldy to transport to the restroom | 5 | 7 | 35 | Minimize material used and considere alternate materials | Chad | Closed- the device is designed to be a perament fixture in the bathroom facilitiy.
12 | Safety | The material used in the device are not chemical resistant/bioresistant | Device would not be able to be properly santitized | The material chosen | 4 | 8 | 32 | Research materials before use to make sure they are able to be disinfectant and sanititized | Kaylie | Closed- based on papers for the materials used, this is not a risk
13 | Technical | Cannot opperate with no/low water pressure | Cannot raise seat/clean and transfer process would be difficult | Plumbing issue, no power to toilet | 1 | 9 | 9 | Have a backup power supply, have a plumber on call | Jared | Closed- the device is currently operating at 25 psi, which is lower than the designed water pressure.
14 | Resource | RIT wifi stops working during group work. | Cant do work on campus/in class | RIT servers go down due to weather or maintance | 4 | 9 | 36 | Plan to work remotely | Hannah | Closed- the wifi here is bad but it was not an issue
15 | Technical | The team has trouble machining some parts due to complex geometry | Purchase replacement part or change desing | The team did not take manufauring into account when desinging | 8 | 9 | 72 | Keep machined parts to a general design and purchase more complex parts | Jared | Closed, all needed parts of the design were able to be machined with little to no issues
16 | Technical | Main design prototype fails and other parts that depend on it have to be redesigned | Revisit drawings and part that failed | The part design was not fully thought through | 9 | 6 | 54 | Make sure parts are tested prior to assembly | Jared | Closed- all redesigning of the device as been completed and the device is functional.
17 | Resource | Client adds a requirement | May need to got back and rethink design | Not clear communication with the the client | 4 | 5 | 20 | Keep in contact with the client throughout the design process | Kaylie | Closed- customer handoff is occuring, no other requirements are being at this time
18 | Resource | Zoom stops working, when we have to go online | The team may not be able to meet with guide, client, other team member | Zoom is constantly having issues | 9 | 3 | 27 | Touch base through other means email, slack | Hannah | Closed- this again has not been an issue over the course of the year
19 | Technical | CAD files get lost | Project files need to be redone, costing valuable time | The program could crash or files get deleted accidentally | 4 | 7 | 28 | Save files regularly, make a backup of all CAD files | Gina | Closed- we have multiple backups of CAD files and this has not been an issue
20 | Technical | Once fabricated the team realizes that the designs are not realistic for the application. | The whole project would be need to be rethough, may need to start from the building | Not enough concept evaluation in earlier phases | 4 | 9 | 36 | The team will make sure to choose concepts that are realistic | Hannah | Closed- the device is functional as designed
21 | Resource | Shipping time will be prolonged due to pandemic | prototype will take longer to assemble | The pandemic has altered shipping times and effency | 7 | 6 | 42 | Must order parts far in advance | Jared | Closed- the end of the semester and no more parts are being ordered
22 | Resource | Google services stop working | our files on the drive are inaccessible | hardware/software failure in google's data centers | 4 | 9 | 36 | Refresh the page | Bing/Yahoo | Closed- this was unlikely to happen and it hasnt
23 | Resource | Can not work with an ID student on device design | Can not pick their brain for design ideas | They are busy or don't want to help us | 3 | 3 | 9 | Reach out to an ID student early before they become really busy | Kaylie | Closed-Kimberly has agreed to work with us during MSD II as well
24 | Technical | Product fails/fatigues over time | Becomes dangerous, cant support a person | Overuse, weight capacity is exceeded | 6 | 9 | 54 | Develope a way to fix or maintain the device over time | Jared | Closed- testing was conducted and this type of failure was not evident
25 | Safety | Device falls on a MSD team member | Possible injury or even death | It is pushed over | 1 | 3 | 3 | Be mindful of device balance during assembly/use | Chad | Closed- end of the semester and this has not happened.
26 | Resource | Materials go missing | Have to redo machine or purchase the part | Not properly labeled and they go to scrap | 4 | 9 | 36 | Label everything | Hannah | Closed- materials have not gone missing throughout the semester.
27 | Safety | Team member gets Tetanus | Team member gets Tetanus | Parts from previous designs are rusty | 3 | 6 | 18 | Use appropriate PPE when handling rusty parts | Chad | Closed- we will find out later if this occured
28 | Safety | Team member gets injured in Machine Shop | Chance for serious injury, delay in machining parts | 4/5 team members dont use shop machines very often and 1 is untrained in Machine Shop | 5 | 5 | 25 | Follow all procedures and make sure team members are up to date on training and usage | Jared | Closed- all machining of the materials has been completed with no injuries
29 | Technical | Our seat plate that we machined using an outside source is not to spec | lose time, would have to find new source to get quote from | did not focus on our part, rushed | 1 | 9 | 9 | Make sure we choose a reliable machine shop | Jared | Closed- we were able to machine the seat plate in house
30 | Resource | Machine needed in Machine shop is down | Delays in assembly | Circumstances outside of our control | 8 | 5 | 40 | Plan out jobs in advance to avoid delays | Hannah | Closed- waterjet was down, but we used the plamsa cutter instead
31 | Technical | Unable to decrease minimum weight needed to lower seat lift compared to previous teams | Cannot meet needs from expected customer base | Does not meet customer requirements, not an effective prototype | 2 | 5 | 10 | Complete testing and meet with Subject Matter Experts | Gina | Closed- no minmium weight was needed to operate device.
32 | Technical, Resource, Safety | Previous Teams design decisions and plans | Team member suffers stress-induced illness (possible brain hemorrhage) | Previous Teams design decisions and plans are impossible to understand, causing extreme stress | 4 | 9 | 45 | If a design or plan created by the previous team did not make any sense whatsoever, give up on trying to understand it. Instead, do something that does make sense and will work. | Chad | Closed- we understand last years design however they were stress-inducing
33 | Safety, Resource | Pumpkin carving | Team member might be injured | Team member cuts themself when using knife | 2 | 3 | 6 | Be careful when using knives | Chad | closed- was a grand-ol'time
34 | Technical | Hydraulic system | System excessively leaks during operation | Cylinders and hosing are not appropriately sealed | 3 | 4 | 12 | Investigate applicable sealants | Chad | Closed- leaking of the hydraulic system was minimal and was fixed with teflon tape
35 | Techincal | Hydraulic system are at different heights, or does both hydraulics do not operate in unison | The hydraulics mounts may need to be redesign and/or the tubing needs to be readjusted | The different hydraulic components were machined to different heights | 5 | 5 | 25 | Careful machine component and adjust as neccasrely after assembly | Gina | Closed- the hydraulics do not operate in union based on other issues that will need to be addressed by next years team .
36 | Technical | O-rings in hydraulics need to be replaced | The hydraulics are leaking due to o-rings | Wear and tear from repeatedly taking apart hydraulics, new o-rings need to be purchased | 6 | 3 | 18 | Replaced worn O-rings | Kaylie | Closed - Replaced O-rings
37 | Technical, Safety | Hydraulic system not moving as smooth as anticipated | Can be uncomfortable for user, make use more difficult, and cause more wear on the hydraulic systems | There were one too many o-rings on the hydraulics causing the movement to be less smooth | 5 | 6 | 30 | Removed one O-ring by taking apart hydraulics to help create smoother movements | Kaylie | Closed - Hydraulics were reassembled and tested.
38 | Technical, Safety | The current design of the arm and torso are not feasible | The user may feel uncomfortable using the device if these are lacking | The height of the arm shaft plus the CAD for the torso bar do not translate in real life. Also possibility of tipping forward with current torso bar design | 7 | 4 | 28 | Redesigned arms to be easier for the user. Redesigning torso bar | Kaylie | Closed- the arm was machined and attached, the torso bar wasnt feasible with the materials the team had.