## Phase 2
P21068 MSD I Schedule
PROJECT TITLE |  | Robot Art Assistant
Team Number |  | P21068 | DATE
WBS NUMBER | TASK TITLE | TASK OWNER | PHASE ONE |  | PHASE TWO |  |  |  | PHASE THREE |  |  |  |  | PHASE FOUR |  |  | CUSTOMER HAND-OFF
|  |  | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15
1 | Build & Test Prep
2021-08-30 | Risk and Problem Tracking | bar: PHASE ONE WEEK 1 to PHASE ONE WEEK 2
2021-08-30 | Test Plan Summary | All | bar: PHASE ONE WEEK 1 to PHASE ONE WEEK 2
2021-08-30 | Review BOM | All | bar: PHASE ONE WEEK 1 to PHASE ONE WEEK 2
2021-09-01 | Build and Test Prep Review | All | bar: PHASE ONE WEEK 2
2 | Subsystem- Level Functional Demo & Review
User Interface
| Have UI designed | David | bar: PHASE ONE WEEK 2 to PHASE TWO WEEK 6
| Buttons can be read | Andrew | bar: PHASE ONE WEEK 1 to PHASE TWO WEEK 4
| Joystick can be read | Andrew | bar: PHASE ONE WEEK 1 to PHASE TWO WEEK 4
Motor
| have motors moving | Josh | bar: PHASE ONE WEEK 1 to PHASE TWO WEEK 3
Control
| move motors specific ammount | Josh | bar: PHASE TWO WEEK 3 to PHASE THREE WEEK 7
| move servos | Josh | bar: PHASE TWO WEEK 3 to PHASE THREE WEEK 7
Power
| Outputting correct voltages | Allison, Dylan | bar: PHASE TWO WEEK 4 to PHASE TWO WEEK 6
| Having all parts | Allison, Dylan | bar: PHASE ONE WEEK 1 to PHASE TWO WEEK 4
Belt
| Have all parts | Josh | bar: PHASE ONE WEEK 1 to PHASE TWO WEEK 6
Mechanical
| Have all parts | George | bar: PHASE TWO WEEK 4
Frame attached to base plate | bar: PHASE TWO WEEK 4 to PHASE TWO WEEK 6
| Parts Cut | Josh, John, George | bar: PHASE TWO WEEK 4 to PHASE TWO WEEK 6
Gripper
| Have gripper printed | Josh | bar: PHASE TWO WEEK 4
| Pick stuff up | John | bar: PHASE TWO WEEK 5 to PHASE TWO WEEK 6
| cup printed | Josh | bar: PHASE TWO WEEK 5 to PHASE TWO WEEK 6
2021-09-27 | Subsysem level functional demo and review | bar: PHASE TWO WEEK 6
3 | Preliminary Systems Integration
User Interface
| User interface can control motors | David | bar: PHASE THREE WEEK 8 to PHASE THREE WEEK 10
| Design circuit board for joystick | Andrew | bar: PHASE THREE WEEK 7 to PHASE THREE WEEK 8
| Design circuit board for student input | Andrew | bar: PHASE THREE WEEK 7 to PHASE THREE WEEK 8
| Make Enclosure for student input | Andrew | bar: PHASE THREE WEEK 9 to PHASE FOUR WEEK 12
| Make Enclosure for joystick | Andrew | bar: PHASE THREE WEEK 9 to PHASE FOUR WEEK 12
| Joystick can be read | David | bar: PHASE THREE WEEK 8
| Buttons can be read | David | bar: PHASE THREE WEEK 8
Motor
| mount motors to framework | Josh | bar: PHASE THREE WEEK 8 to PHASE FOUR WEEK 12
Control
| Test motors with on frame with buttons | Andrew | bar: PHASE THREE WEEK 8 to PHASE THREE WEEK 10
Power
| AC/DC - Buck Converter Test | Allison | bar: PHASE TWO WEEK 6 to PHASE THREE WEEK 10
| Motor test with fuses & power | Andrew, Allison | bar: PHASE THREE WEEK 7 to PHASE THREE WEEK 8
| Servo test with fuses & power | Andrew, Allison | bar: PHASE THREE WEEK 7 to PHASE THREE WEEK 8
| Electronics Enclosure Layout | Dylan, Andrew, Allison | bar: PHASE THREE WEEK 7 to PHASE THREE WEEK 8
| Mount Electronics in Enclosure | Dylan, Andrew, Allison | bar: PHASE THREE WEEK 9 to PHASE THREE WEEK 11
| Wire Electronics in Enclosure | Andrew, Dylan, Allison | bar: PHASE THREE WEEK 9 to PHASE FOUR WEEK 13
| Electronics Heat Test | Allison, Andrew | bar: PHASE THREE WEEK 10
| Electronics enclosure layout | Dylan, Andrew, Allison | bar: PHASE THREE WEEK 10
| Electronics are safely stored | Dylan, Andrew, Allison | bar: PHASE THREE WEEK 10 to PHASE FOUR WEEK 12
Belt
| Assemble belts | Josh | bar: PHASE THREE WEEK 8 to PHASE THREE WEEK 10
| Belt enclosures are made | Josh | bar: PHASE THREE WEEK 10
| Test motors with belts on device | Josh | bar: PHASE THREE WEEK 8 to PHASE THREE WEEK 10
Mechanical
| glue 3dp slider parts together | Josh, John | bar: PHASE THREE WEEK 7; PHASE THREE WEEK 10
| glue delrin bushings into 3dp slider parts | Josh, John | bar: PHASE THREE WEEK 7
| bolt feet to framework | George | bar: PHASE THREE WEEK 7 to PHASE THREE WEEK 8
| drill and tap rod ends 1/4-20 | John | bar: PHASE THREE WEEK 7 to PHASE THREE WEEK 8
| cut rods to length | John | bar: PHASE THREE WEEK 7 to PHASE THREE WEEK 8
| drill 1/4" holes in vertical rod supports | George | bar: PHASE THREE WEEK 7 to PHASE THREE WEEK 8
| Parts assembled | John, Josh, George | bar: PHASE THREE WEEK 7 to PHASE THREE WEEK 10
| cut wheelchair table | George | bar: PHASE THREE WEEK 7
Gripper
| Design jaw | John | bar: PHASE THREE WEEK 9 to PHASE THREE WEEK 10
| Improve range of motion | John | bar: PHASE THREE WEEK 9 to PHASE THREE WEEK 10
Paperwork
| Drawings can be made without automatic tool change | Team | bar: PHASE THREE WEEK 9 to PHASE THREE WEEK 10
| Draft paper done | Team | bar: PHASE THREE WEEK 8 to PHASE THREE WEEK 10
| Draft poster done | Team | bar: PHASE THREE WEEK 8 to PHASE THREE WEEK 10
| Draft video done | Team | bar: PHASE THREE WEEK 8 to PHASE THREE WEEK 10
2021-11-01 | Preliminary Systems Integration Functional Demo and review | bar: PHASE THREE WEEK 10
4 | Complete Systems Integration
User Interface
| Make Enclosure for student input | Andrew | bar: PHASE THREE WEEK 11 to PHASE FOUR WEEK 12
| Make Enclosure for joystick | Andrew | bar: PHASE THREE WEEK 11 to PHASE FOUR WEEK 12
| Make enclosure for teacher input | Andrew | bar: PHASE THREE WEEK 11 to PHASE FOUR WEEK 12
Motor
| Mount motors to framework | Josh | bar: PHASE THREE WEEK 11 to PHASE FOUR WEEK 12
Control
| Add homing and page limits | Andrew | bar: PHASE FOUR WEEK 13 to PHASE FOUR WEEK 14
| Limit switches | Andrew | bar: PHASE FOUR WEEK 13 to PHASE FOUR WEEK 14
| Color code wires | John | bar: PHASE FOUR WEEK 13
Power
| Mount Electronics in Enclosure | Dylan, Andrew, Allison | bar: PHASE THREE WEEK 11
| Wire Electronics in Enclosure | Andrew, Dylan, Allison | bar: PHASE THREE WEEK 11 to PHASE FOUR WEEK 13
| Electronics are safely stored | Dylan, Andrew, Allison | bar: PHASE THREE WEEK 11 to PHASE FOUR WEEK 12
Belt
| Assemble belts | Josh | bar: PHASE THREE WEEK 11 to PHASE FOUR WEEK 14
| Belt enclosures are made | Josh | bar: PHASE THREE WEEK 11 to PHASE FOUR WEEK 14
| Test motors with belts on device | Josh | bar: PHASE THREE WEEK 11 to PHASE FOUR WEEK 14
Mechanical
| glue 3dp slider parts together | Josh, John | bar: PHASE THREE WEEK 11
| Parts assembled | John, Josh, George | bar: PHASE THREE WEEK 11 to PHASE FOUR WEEK 14
Gripper
| 3D print parts | John | bar: PHASE THREE WEEK 11 to PHASE FOUR WEEK 14
| Assemble belts | John | bar: PHASE THREE WEEK 11 to PHASE FOUR WEEK 14
Paperwork
| Paper | Team | bar: PHASE THREE WEEK 11 to PHASE FOUR WEEK 14
| Poster | Allison | bar: PHASE THREE WEEK 11 to PHASE FOUR WEEK 14
| Video | Allison, John, Dylan | bar: PHASE THREE WEEK 11 to PHASE FOUR WEEK 14

## Phase 1
P21068 MSD I Schedule
PROJECT TITLE |  | Robot Art Assistant
Team Number |  | P21068 | [5 empty] | DATE | [8 empty] | 2021-12-07 17:42
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION (hrs) | DEPENDENCIES | PCT OF TASK COMPLETE | PHASE ONE | [20 empty] | PHASE TWO | [29 empty] | PHASE THREE | [22 empty] | PHASE FOUR
[8 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15
[8 empty] | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su
1 | Problem Definition | time axis 2021-01-25 to 2021-05-09
1.1 | Project Summary | Allison M. | 2021-02-04 | 2021-02-09 | 1.5 |  | 100% | bar: 2021-02-04 to 2021-02-08
1.2 | Use Cases | David N. | 2021-02-07 | 2021-02-09 | 3 |  | 100% | bar: 2021-02-07 to 2021-02-08
1.3 | Project Goals and Key Deliverables | Kaitlyn P | 2021-02-08 | 2021-02-09 | 0.5 |  | 100% | bar: 2021-02-08
1.4 | Customer Requirements | Josh K. | 2021-02-04 | 2021-02-09 | 2 |  | 100% | bar: 2021-02-04 to 2021-02-08
1.5 | Engineering Requirements | John O. | 2021-02-08 | 2021-02-09 | 2 | 1.4 | 100% | bar: 2021-02-08
1.6 | House of Quality | Andrew P. | 2021-02-05 | 2021-02-09 | 2 | 1.4,1.5 | 100% | bar: 2021-02-05 to 2021-02-08
1.7 | Design Review Materials | George H. | 2021-02-04 | 2021-02-09 | 0.5 |  | 100% | bar: 2021-02-04 to 2021-02-08
1.8 | Plans for next phase | TEAM | 2021-02-10 | 2021-02-09 | 2 | 1.7 | 100% | bar: 2021-02-10
2 | System Level Design
2.1 | Functional Decomposition | Josh | 2021-02-18 | 2021-03-09 | 1 |  | 100% | bar: 2021-02-18 to 2021-03-09
2.2 | Benchmarking | David | 2021-03-04 | 2021-03-09 | 2 |  | 100% | bar: 2021-03-04 to 2021-03-09
2.2.1 | Benchmark Gripper | Dylan, John | 2021-03-03 | 2021-03-04 | 2 |  | 100% | bar: 2021-03-03 to 2021-03-04
2.2.2 | Benchmark Controls/Joysticks | Allison | 2021-03-03 | 2021-03-04 | 2 |  | 100% | bar: 2021-03-03 to 2021-03-04
2.2.3 | Benchmark Wheelchair attachment methods | George | 2021-03-03 | 2021-03-04 | 2 |  | 100% | bar: 2021-03-03 to 2021-03-04
2.2.4 | Benchmark movement systems | Josh, David | 2021-03-03 | 2021-03-04 | 2 |  | 100% | bar: 2021-03-03 to 2021-03-04
2.2.5 | Benchmark paper securing systems | Dylan | 2021-03-03 | 2021-03-04 | 1.5 |  | 100% | bar: 2021-03-03 to 2021-03-04
2.2.6 | Benchmark micro controllers | Andrew, David | 2021-03-03 | 2021-03-04 | 2 |  | 100% | bar: 2021-03-03 to 2021-03-04
2.2.7 | Benchmark aide/teacher input | Andrew | 2021-03-02 | 2021-03-04 | 1 |  | 100% | bar: 2021-03-02 to 2021-03-04
2.3 | Concept Development | TEAM | 2021-02-16 | 2021-02-18 |  | 2.1 | 100% | bar: 2021-02-16 to 2021-02-18
2.4 | Feasibility: Prototyping, Analysis, Simulation |  | 2021-03-07 | 2021-03-11 |  |  | 75% | bar: 2021-03-07 to 2021-03-11
2.4.1 | Analyze power consumption | Allison | 2021-03-09 | 2021-03-11 | 2 | 2.2.6 | 50% | bar: 2021-03-09 to 2021-03-11
2.4.2 | Protoype ways to hold utensil | Dylan, John, George | 2021-03-09 | 2021-03-11 | 5 | 2.2.1 | 80% | bar: 2021-03-09 to 2021-03-11
2.4.3 | Prototype ways to secure the paper | Dylan, Andrew | 2021-03-07 | 2021-03-11 | 5 | 2.2.5 | 100% | bar: 2021-03-07 to 2021-03-11
2.4.4 | Prototype belt system | John, Josh | 2021-03-08 | 2021-03-11 | 4 |  | 100% | bar: 2021-03-08 to 2021-03-11
2.5 | Morphological Chart and Concept Selection | Allison | 2021-03-08 | 2021-03-09 | 1.5 | 2.3 | 100% | bar: 2021-03-08 to 2021-03-09
2.6 | Systems Architecture | Andrew | 2021-03-10 | 2021-03-11 | 2 | 2.5 | 100% | bar: 2021-03-10 to 2021-03-11
2.7 | Designs and Flowcharts | Andrew | 2021-03-10 | 2021-03-11 | 3 | 2.5, 2.6 | 100% | bar: 2021-03-10 to 2021-03-11
2.8 | Risk Assessment | Josh | 2021-03-10 | 2021-03-11 | 0.5 |  | 100% | bar: 2021-03-10 to 2021-03-11
2.9 | Design Review Materials | TEAM | 2021-03-11 | 2021-03-11 | 2 |  | 100% | bar: 2021-03-11
2.10 | Plans for next phase | TEAM | 2021-03-11 | 2021-03-11 | 2 |  | 100% | bar: 2021-03-11
3 | Preliminary Detailed Design
3.1 | Prototyping Engineering Analysis, Simulation |  |  | 2021-04-01 |  |  | 0%
3.A | User Interface subsystem | David, Andrew |  |  |  |  | 0%
3.A.1 | Draw Teacher Input Screens | David | 2021-03-18 | 2021-03-23 | 1 |  | 100% | bar: 2021-03-18 to 2021-03-23
3.A.2 | BOM - student input | Andrew | 2021-03-23 | 2021-03-25 | 2 | 3.A.3 | 90% | bar: 2021-03-23 to 2021-03-25
3.A.3 | Benchmark Microcontrollers | David | 2021-03-23 | 2021-03-25 | 2 |  | 100% | bar: 2021-03-23 to 2021-03-25
3.A.4 | BOM - teacher input | David | 2021-03-25 | 2021-03-30 |  | 3.A.3 | 100% | bar: 2021-03-25 to 2021-03-30
3.A.5 | Block Diagram | Andrew | 2021-03-25 | 2021-03-30 |  | 3.A.3 | 100% | bar: 2021-03-25 to 2021-03-30
3.A.6 | Determine Programming Language | David, Andrew | 2021-03-19 | 2021-03-23 | 1 | 3.A.3 | 100% | bar: 2021-03-19 to 2021-03-23
3.B | Control subsystem | Andrew, David |  |  |  |  | 0%
3.B.1 | Determine Motor Controller | Andrew | 2021-03-25 | 2021-03-30 | 3 | 3.C.2, 3.C.1 | 90% | bar: 2021-03-25 to 2021-03-30
3.B.2 | BOM | David | 2021-03-25 | 2021-03-30 |  | 3.B.1,3.B.5 | 100% | bar: 2021-03-25 to 2021-03-30
3.B.3 | Drawing of Control System | David | 2021-03-30 | 2021-04-06 |  | 3.B.4, 3.B.2 | 100% | bar: 2021-03-30 to 2021-04-06
3.B.4 | Schematic of Circuit | Andrew | 2021-03-31 | 2021-04-01 | 2 | 3.B.1,3.B.5 | 90% | bar: 2021-03-31 to 2021-04-01
3.B.5 | Benchmark Encoders | Andrew | 2021-03-19 | 2021-03-23 | 2 |  | 100% | bar: 2021-03-19 to 2021-03-23
3.C | Motor subsystem | Josh, George, David |  |  |  |  | 0%
3.C.1 | Determine motor drives | George, David |  | 2021-04-01 |  | 3.C.2 | 0%
3.C.2 | Determine motor | Josh, George, David |  |  |  |  | 100%
3.C.3 | Bill of Material (BOM) | Josh |  |  |  | 3.C.2 | 0%
3.D | Mechanical subsystem | John, Josh, George |  |  |  |  | 0%
3.D.1 | Student input mount on wheelchair | George, Josh | 2021-03-23 | 2021-04-08 |  |  | 100% | bar: 2021-03-23
3.D.2 | Bill of Material (BOM) | John |  |  |  | 3.D.3, | 0%
3.D.3 | Material Framework (8020,etc) | Josh, John |  |  |  |  | 0%
3.D.4 | Better Prototype of paper securing | George | 2021-03-23 | 2021-04-08 |  |  | 100% | bar: 2021-03-23
3.D.5 | Attachment of motors and grippers | Josh |  |  |  | 3.C.2, 3.G.4 | 100%
3.D.6 | 3d model of device | John, Josh |  |  |  | 3.D.3, 3.D.5, 3.D.4 | 50% | bar: 2021-03-25 to 2021-04-06
3.E | Power subsystem | Allison, Dylan |  |  |  |  | 75%
3.E.1 | Research batteries | Allison, Dylan | 2021-03-25 | 2021-03-30 |  | 3.E.2 | 100%
3.E.2 | Determine power requirements | Allison | 2021-03-23 | 2021-03-28 |  | 3.C.1, 3.C.2, 3.B.1, 3.A.3, 3.G.5 | 100% | bar: 2021-03-23 to 2021-03-25
3.E.3 | Bill of Material (BOM) | Dylan | 2021-03-30 | 2021-04-01 |  | 3.E.5 | 50%
3.E.4 | Block diagram | Allison, Dylan | 2021-03-30 | 2021-04-01 |  | 3.E.2, 3.E.1 | 100%
3.E.5 | Schematics | Allison, Dylan | 2021-04-01 | 2021-04-06 |  | 3.E.4 | 0%
3.F | Belt subsystem | Josh, George |  |  |  |  | 0%
3.F.1 | BOM | Josh |  |  |  | 3.F.2 | 50%
3.F.2 | Schematic of Belt Design | Josh, George |  |  |  |  | 100%
3.G | Gripper subsystem | Dylan, John |  |  |  |  | 0%
3.G.1 | Bill of materials | Dylan |  | 2021-04-01 |  | 3.G.3, 3.G.4 | 0%
3.G.2 | Prototype of gripper | Dylan, John | 2021-03-23 | 2021-03-30 |  | 3.G.3, 3.G.4, 3.G.5 | 50% | bar: 2021-03-23 to 2021-04-06
3.G.3 | Determine off shelf option | Dylan, John | 2021-03-23 | 2021-03-23 |  |  | 100% | bar: 2021-03-23
3.G.4 | Schematic of gripper | John | 2021-03-23 | 2021-03-25 |  | 3.G.5, 3.G.3 | 100%
3.G.5 | Determine servos to use | Dylan | 2021-03-23 | 2021-03-23 |  |  | 100% | bar: 2021-03-23
3.G.6 | 3D model of gripper | John | 2021-03-23 | 2021-04-01 |  | 3.G.4 | 75% | bar: 2021-03-23 to 2021-04-06
3.H | Extra bits | [5 empty] | 0%
3.H.1 | Research automatic tool changer | Dylan, Allison | 2021-03-18 | 2021-03-25 |  |  | 60% | bar: 2021-03-18 to 2021-03-25
3.H.2 | Schematic of cup | Allison, Dylan | 2021-03-25 |  |  | 3.H.1 | 40%
3.H.3 | Carrying case design | Andrew |  |  |  | 3.D.6 | 0%
3.2 | Feasibility: Prototyping, Analysis, Simulation |  |  | 2021-04-01 |  |  | 0%
3.3 | Drawings, Schematics, Flow Charts, Simulations, etc. |  |  | 2021-04-01 |  |  | 0%
3.4 | Bill of Material (BOM) |  |  | 2021-04-01 |  |  | 0%
3.5 | Test Plans |  |  | 2021-04-01 |  |  | 0%
3.5.1 | User interface tests | Andrew, David |  |  |  |  | 0%
3.5.2 | control tests | Andrew, David |  |  |  |  | 0%
3.5.3 | motor tests | Josh |  |  |  |  | 0%
3.5.4 | mechanical tests | John, Josh, George |  |  |  |  | 0%
3.5.5 | power tests | Allison |  |  |  |  | 0%
3.5.6 | belts tests | Josh |  |  |  |  | 0%
3.5.7 | gripper tests | Dylan, John |  |  |  |  | 0%
3.6 | System Design and Flowcharts/System Block Diagram |  |  | 2021-04-01 |  |  | 0%
3.7 | Update Confluence format | Andrew | 2021-03-18 | 2021-03-23 | 0.5 |  | 75% | bar: 2021-03-18 to 2021-03-23
3.8 | Set up BOM/Purchasing Process | Allison | 2021-03-18 | 2021-03-23 | 1 |  | 90%
3.9 | Risk Assessment |  | 2021-04-06 | 2021-04-06 | 1 |  | 100%
3.10 | Design Review Materials |  | 2021-04-06 | 2021-04-06 | 1 |  | 100%
3.11 | Plans for next phase | TEAM |  | 2021-04-01 |  |  | 0%
4 | Detailed Design
4.A | User Interface subsystem | David, Andrew |  |  |  |  | 0%
4.A.1 | Order Components | Allison |  |  |  |  | 0%
4.A.2 | Test bench student input | Andrew |  |  |  |  | 0%
4.A.3 | Create PCB Design | Andrew |  |  |  |  | 0%
4.A.4 | Start Developing Code | David |  |  |  |  | 0%
4.B | Control subsystem | Andrew, David |  |  |  |  | 0%
4.B.1 | Order Components | Allison |  |  |  |  | 0%
4.B.2 | Test Components | Andrew |  |  |  |  | 0%
4.B.3 | Start Developing Code | David |  |  |  |  | 0%
4.C | Motor subsystem | Josh, George, David |  |  |  |  | 0%
4.C.1 | Test with controller and belts | Josh, David |  |  |  |  | 0%
4.C.2 | Update belt design | Josh |  |  |  |  | 0%
4.C.3 | Order Components | Allison |  |  |  |  | 0%
4.D | Mechanical subsystem | John, Josh, George |  |  |  |  | 0%
4.D.1 | Student input mount on wheelchair | George |  |  |  |  | 0%
4.D.2 | Bill of materials | [5 empty] | 0%
4.D.3 | Material Framework (8020,etc) | [5 empty] | 0%
4.D.4 | Better Prototype of paper securing | [5 empty] | 0%
4.D.5 | Attachment of motors and grippers | [5 empty] | 0%
4.D.6 | 3d model of device | Josh |  |  |  |  | 0%
4.D.7 | Order Components | Allison |  |  |  |  | 0%
4.D.8 | Determine System Weight | Josh |  |  |  |  | 0%
4.E | Power subsystem | Allison, Dylan |  |  |  |  | 0%
4.E.1 | Bill of materials | Allison |  |  |  |  | 0%
4.E.2 | Schematics | Allison, Dylan |  |  |  |  | 0%
4.E.3 | Order Components | Allison |  |  |  |  | 0%
4.F | Belt subsystem | Josh, George |  |  |  |  | 0%
4.F.1 | Update bill of materials | Josh |  |  |  |  | 0%
4.F.2 | Update schematic for dual belts | Josh |  |  |  |  | 0%
4.F.3 | Order Components | Allison |  |  |  |  | 0%
4.F.4 | Determine System Weight | Josh |  |  |  |  | 0%
4.F.5 | Test belt drive with motors | Josh |  |  |  |  | 0%
4.G | Gripper subsystem | Dylan, John |  |  |  |  | 0%
4.G.1 | Bill of materials | John |  |  |  |  | 0%
4.G.2 | Prototype of gripper | John, Dylan |  |  |  |  | 0%
4.G.3 | [6 empty] | 0%
4.G.4 | Schematic of gripper | John |  |  |  |  | 0%
4.G.5 | [6 empty] | 0%
4.G.6 | 3d model of gripper | John, Dylan |  |  |  |  | 0%
4.G.7 | Prototype of cup | Dylan |  |  |  |  | 0%
4.I | Test Plans | [5 empty] | 0%
4.I.1 | User Interface Tests | [5 empty] | 0%
4.I.2 | Control Tests | [5 empty] | 0%
4.I.3 | Motor Subsystem | [5 empty] | 0%
4.I.4 | Mechanical subsystem | [5 empty] | 0%
4.I.5 | Power Subystem | [5 empty] | 0%
4.I.6 | Belt Subsystem | [5 empty] | 0%
4.I.7 | Gripper Subsystem | [5 empty] | 0%
4.2 | Prototyping Engineering Analysis, Simulation | [5 empty] | 0%
4.3 | Drawings, Schematics, Flow Charts, Simulations, etc. | [5 empty] | 0%
4.4 | Bill of Material (BOM) | [5 empty] | 0%
| Test Plans | [5 empty] | 0%
3.3.1 | System Design and Flowchars/System Block Diagram | [5 empty] | 0%
| Risk Assessment | [5 empty] | 0%
| Design Review Materials | [5 empty] | 0%
| Plans for next phase | TEAM |  |  |  |  | 0%
A | Project Management
A.1 | Intellectual Property Considerations | Andrew P. | 2021-02-05 | 2021-02-09 | 0.5 |  | 100% | bar: 2021-02-05 to 2021-02-08
A.2 | Team Setup | Andrew P. | 2021-02-05 | 2021-02-09 | 1 |  | 100% | bar: 2021-02-05 to 2021-02-08
A.3 | Team Values and Norms | Andrew P. | 2021-02-06 | 2021-02-09 | 2 |  | 100% | bar: 2021-02-06 to 2021-02-08
A.4 | Project Plans & Schedules | Andrew P. | 2021-02-08 | 2021-02-09 | 1 |  | 75% | bar: 2021-02-07 to 2021-02-08
A.5 | Risk Assessment and Growth Curves | Andrew P. | 2021-02-09 | 2021-02-09 | 3 |  | 25% | bar: 2021-02-09
A.6 | Communication | Allison M | 2021-02-08 | 2021-02-09 | 1 |  | 100% | bar: 2021-02-08 to 2021-02-09